## Overview
Cisco Secure Network Analytics (SNA) — 8-Site Deployment
CVS Health — Network Security Engineering
Project Window: September 1, 2026 – June 14, 2027 (~41 weeks, incl. holiday change freeze); Phase 3 scope reconciliation and Phase 4 maturity window open-ended beyond that
Scope
• Deploy 8 independent CSNA environments — each its own Collector + Flow Broker + Storage stack — at Shea, RI1-2100 Corporate, RI1-2100 Retail, EQ-VA, EQ-DAL, Windsor, Middletown, and Vegas
• Reconcile and onboard the 18-firewall / 8-site Phase 2 outlier backlog identified in the netflow_fw_collector_mapping.xlsx dataset (Colo/B2B, PSS mail-order/distribution centers, egress hubs)
• Resolve all open prerequisites (CRIT-1/2/3, ATTN-5/6/7/8) prior to the affected environment's go-live
• Derive all SNA host groups from IPAM ROUTING_DOMAIN / CANONICAL_LOCATION with LM → IPAM → SNA update order enforced
• Stand up domain-scoped Cisco ISE pxGrid subscriptions per environment; build automated ISE quarantine runbooks for the CVS + Aetna enterprise environments (target <2 min round-trip)
• Integrate PAN-OS IPFIX + App-ID and FTD connection logs at CVS/Aetna perimeters
• Integrate Cisco XDR for cross-environment entity correlation and Splunk for domain-tagged long-term retention/hunt
• Activate ETA (Encrypted Traffic Analytics) and Talos threat intelligence; map SNA evidence to HIPAA Technical Safeguards, PCI DSS Req. 10, and SOC 2 CC7.2
• Reconcile the Wood Dale IL / Phoenix AZ / Woodbridge NJ / Atlanta-Sparks NV items named in the original vision doc but absent from current firewall data (Phase 3 — scope not yet determined)
Out of Scope
Physical network tap deployment (design is FC-placement-based by construction); automated/real-time blocking beyond ISE pxGrid quarantine integration; any cross-domain merge of CVS/Aetna pxGrid identity scope; Stack 3 [retail] per-device PCI control (requires in-store endpoint/ISE microsegmentation — a separate program, not SNA); resolution of the underlying IPAM Observed→Inferred data-quality defect itself (SNA program flags it and works around it via naming convention, CCD Platform owns the fix); Cloud (Azure/AWS/GCP) sourcing — not represented in the 8-site model, status open pending ATTN-6 resolution.
Current State → Target State
Dimension | Current State | Target State
Environment architecture | Not deployed | 8 independent per-site CSNA environments (Collector + Flow Broker + Storage), not a shared Manager across sites
Firewall telemetry coverage | 0 of 197 firewalls mapped | 179 of 197 firewalls resolve to a Phase 1 site; 18 (8 sites) tracked as Phase 2 backlog
CVS/Aetna IP collision handling | Unresolved — 45 confirmed collisions (public space, RFC1918, GCP BU allocations, TEST-NET) | Eliminated by construction — no shared environment builds composite baselines across colliding domains
Host group governance | N/A | Derived from IPAM ROUTING_DOMAIN / CANONICAL_LOCATION; LM → IPAM → SNA update order enforced
ISE integration | Not integrated | Domain-scoped pxGrid subscription per environment; automated quarantine (CVS+Aetna enterprise target <2 min)
Cross-environment correlation | N/A | Cisco XDR (entity-based) above SNA; Splunk domain-tagged retention/hunt
Compliance evidence | Manual / gaps | SNA evidences HIPAA Technical Safeguards, PCI DSS Req. 10, SOC 2 CC7.2
Key Assumption
No new-environment cutover or FC activation occurs between Nov 24, 2026 and Jan 4, 2027 (retail peak-season change freeze). Environment baselines already underway (e.g., RI1-2100 Retail) are monitoring-only and may continue passively through the freeze. See 'Phase Schedule' tab.
Source: "Cisco Secure Network Analytics — Enterprise Deployment Vision & Strategy," CVS Health InfoSec / CCD Platform, v1.0, 2026-05-19, corrected against netflow_fw_collector_mapping.xlsx (2026). Program Owner: Michael J. Martin.

## Phase Schedule
Phase # | Workstream | Start Date | End Date | Duration (days) | Duration (weeks) | Notes
0 | Discovery & Prerequisite Resolution | 2026-09-01 | 2026-09-21 | 20 | 2.9 | Resolve CRIT-1/2/3, ATTN-5/7/8; size all 8 environments; design 8x domain-scoped pxGrid
1 | Deploy 8 CSNA Environments | 2026-09-22 | 2026-11-16 | 55 | 7.9 | Shea + RI1-2100 Corporate + RI1-2100 Retail first (highest FW volume), then EQ-VA/EQ-DAL, then Windsor/Middletown, then Vegas
— | Change Freeze / Stabilization Window | 2026-11-17 | 2027-01-04 | 48 | 6.9 | No new environment cutovers or FC activation; baselines already underway continue passively (monitoring-only)
2 | Outlier Site Reconciliation (Phase 2 backlog) | 2027-01-05 | 2027-02-15 | 41 | 5.9 | 18 firewalls / 8 sites: Santa Clara + Atlanta QTS (Colo/B2B), Honolulu + Pittsburgh + San Antonio (PSS mail-order/DC), CME-HUB-PROD/NONPROD + CMC-HUB (egress, location TBD)
3 | Scope Reconciliation — Legacy Vision-Doc Sites | 2027-02-16 | 2027-03-15 | 27 | 3.9 | Confirm current status of Wood Dale IL, Phoenix AZ, Woodbridge NJ, Atlanta/Sparks NV COLO against IPAM/location_master — not in current FW data, scope open
4 | Tuning & Maturity | 2027-03-16 | 2027-06-14 | 90 | 12.9 | Splunk all environments, ISE quarantine runbooks, ETA tuning, SOC 2/PCI/HIPAA evidence mapping, XDR hunt playbooks, retail baseline maturity review

## Task Detail
Phase | Task | Owner | Start Date | End Date | Duration (days) | Status
0 - Discovery & Prerequisite Resolution | Resolve CRIT-3: exclude 11 retail /24 collision blocks from CVS/Aetna enterprise host groups | Michael | 2026-09-01 | 2026-09-07 | 6 | Not Started
0 - Discovery & Prerequisite Resolution | Resolve CRIT-2: confirm RI1-2100 Retail host groups will use store WAN IPs from 128T controller inventory, not retail_networks device records | Michael + CCD Platform team | 2026-09-01 | 2026-09-07 | 6 | Not Started
0 - Discovery & Prerequisite Resolution | Resolve CRIT-1: define per-VRF Flexible NetFlow + ODID tagging plan for Vegas COLO ahead of Phase 1 | Assigned engineer + Switching/COLO team | 2026-09-08 | 2026-09-14 | 6 | Not Started
0 - Discovery & Prerequisite Resolution | Resolve ATTN-5: validate internet egress FC model against actual border router topology | Assigned engineer + Network team | 2026-09-08 | 2026-09-14 | 6 | Not Started
0 - Discovery & Prerequisite Resolution | Resolve ATTN-8: close Observed→Inferred DATA_QUALITY patch (open since IPAM v3.71) or adopt CVS-DC-AUTH/CVS-DC-INFD naming split before enterprise baselining | Assigned engineer + CCD Platform team | 2026-09-01 | 2026-09-14 | 13 | Not Started
0 - Discovery & Prerequisite Resolution | Size and procure Collector + Flow Broker + Storage for all 8 environments | Michael | 2026-09-01 | 2026-09-14 | 13 | Not Started
0 - Discovery & Prerequisite Resolution | Design 8x domain-scoped ISE pxGrid subscription model; confirm CVS/Aetna isolation approach | Assigned engineer + ISE/NAC team | 2026-09-08 | 2026-09-21 | 13 | Not Started
0 - Discovery & Prerequisite Resolution | Build per-site cutover and baseline validation plan for all 8 environments | Michael | 2026-09-15 | 2026-09-21 | 6 | Not Started
1 - Deploy 8 CSNA Environments | Deploy Shea environment (Collector + Flow Broker + Storage); unsampled NetFlow, FTD, PAN-OS IPFIX+App-ID, CVS-scoped pxGrid | Assigned engineer | 2026-09-22 | 2026-10-05 | 13 | Not Started
1 - Deploy 8 CSNA Environments | Deploy RI1-2100 Corporate environment; same telemetry stack as Shea | Assigned engineer | 2026-09-22 | 2026-10-05 | 13 | Not Started
1 - Deploy 8 CSNA Environments | Deploy RI1-2100 Retail environment; NetFlow FC at 128T SD-WAN hub controller, store WAN IP host groups | Assigned engineer + SD-WAN team | 2026-09-29 | 2026-10-12 | 13 | Not Started
1 - Deploy 8 CSNA Environments | Validate Shea + RI1-2100 (Corporate + Retail) host groups against CRIT-2/CRIT-3 exclusions | Team | 2026-10-06 | 2026-10-19 | 13 | Not Started
1 - Deploy 8 CSNA Environments | Deploy EQ-VA environment (Ashburn) — Colo/B2B telemetry sourcing | Assigned engineer | 2026-10-13 | 2026-10-26 | 13 | Not Started
1 - Deploy 8 CSNA Environments | Deploy EQ-DAL environment (Dallas) — Colo/B2B telemetry sourcing | Assigned engineer | 2026-10-13 | 2026-10-26 | 13 | Not Started
1 - Deploy 8 CSNA Environments | Deploy Windsor environment; Aetna-scoped pxGrid subscription, validate isolation from CVS-scoped subscriptions | Assigned engineer + ISE team | 2026-10-20 | 2026-11-02 | 13 | Not Started
1 - Deploy 8 CSNA Environments | Deploy Middletown environment; same Aetna telemetry/pxGrid stack as Windsor | Assigned engineer + ISE team | 2026-10-20 | 2026-11-02 | 13 | Not Started
1 - Deploy 8 CSNA Environments | Deploy Vegas environment; validate CRIT-1 ODID VRF tagging before FC activation | Assigned engineer + Switching/COLO team | 2026-11-03 | 2026-11-09 | 6 | Not Started
1 - Deploy 8 CSNA Environments | Onboard Secure Client NVM telemetry across enterprise environments | Assigned engineer | 2026-10-27 | 2026-11-02 | 6 | Not Started
1 - Deploy 8 CSNA Environments | Validate zero cross-environment IP leakage across all 8; begin 30-day baselines (continue passively into freeze) | Team | 2026-11-03 | 2026-11-16 | 13 | Not Started
1 - Deploy 8 CSNA Environments | Validate detection coverage against SOC red-team exercise (CVS + Aetna enterprise, target ≥85%) | Team | 2026-11-09 | 2026-11-16 | 7 | Not Started
2 - Outlier Site Reconciliation | Confirm Santa Clara (CoreSite) and Atlanta QTS firewall routing — assign to nearest Phase 1 environment or stand up dedicated collection | Michael + Colo team | 2027-01-05 | 2027-01-18 | 13 | Not Started
2 - Outlier Site Reconciliation | Confirm Honolulu, Pittsburgh, San Antonio (PSS mail-order/distribution centers) PCI firewall telemetry routing | Assigned engineer + PSS ops | 2027-01-19 | 2027-02-01 | 13 | Not Started
2 - Outlier Site Reconciliation | Resolve location/ownership of CME-HUB-PROD, CME-HUB-NONPROD, CMC-HUB (no Location/Division in current data) before assigning telemetry routing | Michael + Network team | 2027-01-05 | 2027-01-18 | 13 | Not Started
2 - Outlier Site Reconciliation | Onboard confirmed Phase 2 sites into host groups and assigned environments | Team | 2027-02-02 | 2027-02-08 | 6 | Not Started
2 - Outlier Site Reconciliation | Validate 0 UNMAPPED firewalls remaining across the 197-firewall inventory | Team | 2027-02-09 | 2027-02-15 | 6 | Not Started
3 - Scope Reconciliation: Legacy Vision-Doc Sites | Confirm current status of Wood Dale IL (US_WOI_IL_DC) — active 4th CVS DC or decommissioned — against IPAM/location_master | Michael + CCD Platform team | 2027-02-16 | 2027-02-22 | 6 | Not Started
3 - Scope Reconciliation: Legacy Vision-Doc Sites | Confirm current status of Phoenix AZ and Woodbridge NJ (Aetna DR) sites against IPAM/location_master | Michael + CCD Platform team | 2027-02-23 | 2027-03-01 | 6 | Not Started
3 - Scope Reconciliation: Legacy Vision-Doc Sites | Confirm current status of the Atlanta/Sparks NV COLO pairing (The Keep Campus / Switch TRE) — distinct from the Atlanta QTS site in Phase 2 | Michael + Colo team | 2027-03-02 | 2027-03-08 | 6 | Not Started
3 - Scope Reconciliation: Legacy Vision-Doc Sites | Determine in-scope vs. out-of-scope for each; schedule any in-scope sites as a follow-on phase | Michael | 2027-03-09 | 2027-03-15 | 6 | Not Started
4 - Tuning & Maturity | Onboard all confirmed environments to Splunk (domain-tagged retention, cross-domain hunt) | Assigned engineer + Splunk team | 2027-03-16 | 2027-03-29 | 13 | Not Started
4 - Tuning & Maturity | Build ISE quarantine runbooks for CVS + Aetna enterprise environments (target <2 min round-trip) | Assigned engineer + ISE team | 2027-03-16 | 2027-04-05 | 20 | Not Started
4 - Tuning & Maturity | Tune ETA (cert fingerprinting, beacon detection, DGA detection via DNS flow patterns) | Assigned engineer | 2027-04-06 | 2027-04-19 | 13 | Not Started
4 - Tuning & Maturity | Map SNA evidence to SOC 2 CC7.2, PCI DSS Req. 10, HIPAA Technical Safeguards | Michael + GRC | 2027-04-06 | 2027-04-26 | 20 | Not Started
4 - Tuning & Maturity | RI1-2100 Retail baseline maturity review (90 days post-live) | Team | 2027-04-06 | 2027-04-19 | 13 | Not Started
4 - Tuning & Maturity | Build cross-environment XDR hunt playbooks | Assigned engineer | 2027-04-20 | 2027-05-03 | 13 | Not Started
4 - Tuning & Maturity | Confirm technical success criteria (0 cross-environment collisions, 0 sampled NetFlow, 0 unlabeled Inferred subnets, 0 retail /26 blocks, 0 unvalidated Vegas ODID) | Michael | 2027-05-04 | 2027-05-17 | 13 | Not Started
4 - Tuning & Maturity | Validate operational targets (≥85% SOC detection CVS+Aetna, <10% false positive rate, <15 min MTTD, <2 min ISE quarantine round-trip) | Team | 2027-05-18 | 2027-05-31 | 13 | Not Started
4 - Tuning & Maturity | Establish annual IPAM/site review cadence | Michael | 2027-06-01 | 2027-06-14 | 13 | Not Started
4 - Tuning & Maturity | Program closeout / maturity sign-off | Michael | 2027-06-01 | 2027-06-14 | 13 | Not Started

## Gantt Chart
Workstream | 2026-09-01 | 2026-09-08 | 2026-09-15 | 2026-09-22 | 2026-09-29 | 2026-10-06 | 2026-10-13 | 2026-10-20 | 2026-10-27 | 2026-11-03 | 2026-11-10 | 2026-11-17 | 2026-11-24 | 2026-12-01 | 2026-12-08 | 2026-12-15 | 2026-12-22 | 2026-12-29 | 2027-01-05 | 2027-01-12 | 2027-01-19 | 2027-01-26 | 2027-02-02 | 2027-02-09 | 2027-02-16 | 2027-02-23 | 2027-03-02 | 2027-03-09 | 2027-03-16 | 2027-03-23 | 2027-03-30 | 2027-04-06 | 2027-04-13 | 2027-04-20 | 2027-04-27 | 2027-05-04 | 2027-05-11 | 2027-05-18 | 2027-05-25 | 2027-06-01 | 2027-06-08
0 - Discovery & Prerequisite Resolution | bar: 2026-09-01 to 2026-09-15
1 - Deploy 8 CSNA Environments | bar: 2026-09-22 to 2026-11-10
Change Freeze / Stabilization Window | bar: 2026-11-17 to 2026-12-29
2 - Outlier Site Reconciliation | bar: 2027-01-05 to 2027-02-09
3 - Scope Reconciliation: Legacy Sites (open) | bar: 2027-02-16 to 2027-03-09
4 - Tuning & Maturity | bar: 2027-03-16 to 2027-06-08
Legend:
Active workstream | bar: 2026-09-01
Change freeze / stabilization window | bar: 2026-09-01
Open / scope not yet determined | bar: 2026-09-01

## Risks
Risk | Impact | Mitigation
CRIT-1 not resolved before Vegas FC activation — no ODID VRF tagging | CVS and Aetna flows merge in the Vegas environment, producing unreliable composite baselines | Treat as hard blocker — validate ODID=CVS-VRF/ODID=AETNA-VRF tagging before Vegas FC go-live
CRIT-2 not resolved — RI1-2100 Retail host groups built from retail_networks device records instead of 128T store WAN IPs | 294,341 SNAT-masked internal device IPs added to host groups; noise, no real detection value | Enforce store WAN/tunnel IP as the only valid retail host group key; block retail_networks device-IP import at config review
CRIT-3 not resolved — 11 retail /24 blocks not excluded from CVS/Aetna enterprise host groups | Enterprise baselines contaminated by SNAT-masked retail-internal traffic | Explicit exclusion list (3 Internal-PBM blocks, 8 Internal-HCB blocks) validated in Phase 0 before any enterprise host group is built
ATTN-8 DATA_QUALITY patch remains open at enterprise baselining | Subnets carry unresolved Observed→Inferred ambiguity, weakening baseline confidence | Adopt distinct CVS-DC-AUTH / CVS-DC-INFD naming split if the patch has not resolved by Phase 1 baselining
Phase 2 outlier sites (Santa Clara, Atlanta QTS, Honolulu, Pittsburgh, San Antonio, CME-HUB, CMC-HUB) remain unmapped past Phase 2 close | 18 firewalls stay outside SNA visibility indefinitely, including 3 PCI-scoped mail-order/distribution center pairs | Track as a hard exit criterion for Phase 2 — 0 UNMAPPED firewalls before Phase 2 sign-off
CME-HUB-PROD/NONPROD and CMC-HUB have no Location or Division populated in source data | Cannot assign correct environment or compliance scope without confirming physical site vs. logical aggregation point | Escalate to network/site-inventory owners in Phase 2 before any telemetry routing decision is made
Cross-domain ISE pxGrid subscription scope leak (a CVS-side environment receiving Aetna user-IP mappings, or vice versa) | Identity correlation applied to the wrong domain — the IP collision problem re-introduced at the identity layer | Domain-scoped pxGrid subscription per environment, validated explicitly before each environment's identity integration goes live
RI1-2100 Retail SNAT constraint treated as a deployment defect rather than an architectural ceiling | Stakeholder expectation mismatch — demanding per-device PCI detection SNA cannot provide | Communicate the store-aggregate-only detection scope explicitly in Phase 1 acceptance criteria; per-device control routed to a separate ISE/endpoint microsegmentation program
Retail change freeze (Nov 24, 2026 – Jan 4, 2027) compresses effective working time | Schedule pressure if Phase 1 slips into the freeze window | Phase 1 sequenced to complete by Nov 16; freeze used only for passive baseline continuation, not new cutovers
Wood Dale IL / Phoenix / Woodbridge NJ / Atlanta-Sparks NV COLO named in the original vision doc but absent from current firewall data | Program scope silently expands or a live site is missed if these are assumed resolved without confirmation | Dedicated Phase 3 to confirm current status against IPAM/location_master before scheduling any deployment work for them
East-west L7 payload gap (no physical taps, by design) misread as a coverage failure | Expectation that SNA provides payload-level detection it was never scoped to provide | Document explicitly: NetFlow metadata only; mitigations are ISE microsegmentation, PAN-OS App-ID, and XDR endpoint correlation, not SNA taps

## Open Items
# | Open Item / Decision Needed | Owner | Status
1 | Confirm Collector + Flow Broker + Storage sizing and licensing quote for all 8 Phase 1 environments | TBD | Open
2 | Confirm whether the Nov 24–Jan 4 change freeze assumption (carried over from the Forescout refresh program) applies identically to this program | TBD | Open
3 | Resolve ATTN-8 Observed→Inferred DATA_QUALITY patch owner and target close date (CCD Platform / IPAM team) | TBD | Open
4 | Determine assignment logic for Phase 2 sites — attach to nearest Phase 1 environment vs. stand up dedicated micro-collection | TBD | Open
5 | Confirm physical location and ownership of CME-HUB-PROD, CME-HUB-NONPROD, CMC-HUB (currently no Location/Division in source data) | TBD | Open
6 | Confirm what "PSS" and "PCW" division codes mean organizationally, and whether other PSS/PCW sites beyond Honolulu/Pittsburgh/San Antonio need Phase 2 inclusion | TBD | Open
7 | Confirm current status (active/decommissioned/in-scope) of Wood Dale IL, Phoenix AZ, Woodbridge NJ, and the Atlanta/Sparks NV COLO pairing | TBD | Open
8 | Validate internet egress FC model ("3 CVS + 2 Aetna egress") against actual border router topology (ATTN-5) | TBD | Open
9 | Confirm IPAM governance remediation path for reserved address space in production (1.1.1.0, 203.0.113.0) — do not exclude from host groups in the meantime (ATTN-7) | TBD | Open
10 | Confirm target <2 min ISE quarantine round-trip is achievable given current pxGrid/ISE policy engine latency, or renegotiate the target | TBD | Open
11 | Confirm GRC concurrence that the compliance evidence mapping (HIPAA Technical Safeguards, PCI DSS Req. 10, SOC 2 CC7.2) is complete and sufficient | TBD | Open
12 | Confirm assigned engineering staffing (beyond Michael as Program Owner) for parallel Phase 1 site builds | TBD | Open
13 | Confirm whether/when Cloud (Azure/AWS/GCP) sourcing re-enters scope, given it is not represented in the 8-site model (ATTN-6) | TBD | Open

## Team & Ownership
Role | Name / Group | Responsibility
Program Owner | Michael J. Martin | Architecture correction/design authority, prerequisite/blocker resolution sign-off, cross-team engagement lead, cutover sign-off per environment
Engineer | Assigned engineer(s) | Task execution across environment deployment, telemetry integration, and baseline validation workstreams
Cross-functional dependency | ISE/NAC team | Domain-scoped pxGrid subscription configuration and quarantine runbook integration
Cross-functional dependency | Firewall team (FTD/PAN-OS) | FTD connection log and PAN-OS IPFIX+App-ID integration at CVS/Aetna perimeters
Cross-functional dependency | SD-WAN team | 128T hub controller NetFlow FC configuration for the RI1-2100 Retail environment
Cross-functional dependency | Switching/COLO team | Per-VRF Flexible NetFlow and ODID tagging at Vegas; scope confirmation for the legacy Atlanta/Sparks NV COLO pairing
Cross-functional dependency | Colo team | EQ-VA / EQ-DAL environment coordination; Santa Clara and Atlanta QTS Phase 2 reconciliation
Cross-functional dependency | PSS ops | Honolulu, Pittsburgh, San Antonio mail-order/distribution center PCI firewall telemetry routing
Cross-functional dependency | CCD Platform / IPAM team | ROUTING_DOMAIN, CANONICAL_LOCATION, and DATA_QUALITY governance; LM → IPAM → SNA update sequencing
Cross-functional dependency | Splunk team | Domain-tagged index/retention configuration for cross-domain hunt
Cross-functional dependency | GRC | SOC 2 / PCI DSS / HIPAA evidence mapping and concurrence