## Overview
Forescout NAC Hardware Refresh & Integration Project
CVS Health — Network Security Engineering
Project Window: September 1, 2026 – February 15, 2027 (24 weeks)
Scope
• Decommission the 12 existing Forescout appliances
• Deploy 6 new appliances (consolidated footprint)
• Integrate Jamf + Intune as authoritative asset management sources
• Integrate Tanium, Qualys, CrowdStrike for security posture validation
• Implement MFA for Forescout administrative access via SAML (Ping Identity)
• Implement NiFi ingestion → Splunk logging/telemetry pipeline
• Build a standardized RADIUS MAB configuration template
• Integrate with Palo Alto egress firewalls for Internet egress enforcement
• Integrate DHCP forwarding with switching infrastructure
• Enable RAPD (Rogue Access Point Detection) via Forescout physical switch-layer visibility paired with Cisco Catalyst Center RF-layer detection — detection/alerting only
Out of Scope
RADIUS 802.1X (non-MAB) policy redesign, Claroty/IoT-OT posture work, CCD EDL/source-of-truth catalog changes, and automated rogue containment (wireless deauth, wired port shutdown) — the latter is a later NAC/ZTNA program decision requiring legal/operational review, not part of this window.
Current State → Target State
Dimension | Current State | Target State
Appliance count | 12 appliances | 6 appliances (consolidated)
Asset management sources | Not confirmed / legacy MDM feed | Jamf + Intune (authoritative)
Posture validation sources | Tanium, Qualys, CrowdStrike (existing) | Same three, re-validated post-migration
Admin access control | Standard local/AD credential login | SAML-based MFA via Ping
Logging/telemetry | Not centrally piped / ad hoc | NiFi ingestion pipeline → Splunk
Non-802.1X device auth | No standardized approach | Templated RADIUS MAB configuration
Egress enforcement | Not integrated with NAC posture | Palo Alto egress FW enforcing on Forescout state
DHCP visibility | Not integrated with switching | DHCP forwarding integrated with switch infrastructure
Rogue AP detection (RAPD) | Armis; static authorized-AP list; RF-layer only, switch-layer correlation unconfirmed | Forescout (physical switch-layer) + Cisco Catalyst Center (RF-layer, dynamic); detection/alerting only
Key Assumption
No production cutover, enforcement change, or appliance removal occurs between Nov 24, 2026 and Jan 4, 2027 (Thanksgiving through New Year change freeze). See 'Phase Schedule' tab.

## Phase Schedule
Phase # | Workstream | Start Date | End Date | Duration (days) | Duration (weeks) | Notes
0 | Discovery & Design | 2026-09-01 | 2026-09-28 | 28 | 4 | Covers design for all 8 integration workstreams
1 | New Hardware Deployment (6 appliances) | 2026-09-29 | 2026-11-02 | 35 | 5
4 | MFA Admin Access (SAML/Ping) | 2026-09-29 | 2026-11-02 | 35 | 5 | Independent track, not on hardware critical path
8 | DHCP Forwarding Integration w/ Switching | 2026-10-06 | 2026-11-09 | 35 | 5
2 | Asset Mgmt Integration (Jamf + Intune) | 2026-10-13 | 2026-11-16 | 35 | 5
3 | Posture Integration (Tanium/Qualys/CrowdStrike) | 2026-10-13 | 2026-11-16 | 35 | 5
6 | RADIUS MAB Configuration Template | 2026-10-13 | 2026-11-09 | 28 | 4
5 | Logging & Telemetry (NiFi + Splunk) | 2026-10-13 | 2026-11-23 | 42 | 6
7 | Palo Alto Egress FW Integration | 2026-10-27 | 2026-12-07 | 42 | 6 | Depends on Phase 0 decision: User-ID vs. tag/EDL
11 | RAPD Detection Enablement (Forescout + Catalyst Center) | 2026-11-10 | 2026-12-07 | 28 | 4 | Detection/SOC alerting only; containment deferred to a later phase
— | Change Freeze / Stabilization Window | 2026-11-24 | 2027-01-04 | 42 | 6 | No production cutover activity; validation/rehearsal only
9 | Cutover (all sites) | 2027-01-05 | 2027-01-25 | 21 | 3
10 | Decommission (12 legacy appliances) | 2027-01-26 | 2027-02-15 | 21 | 3

## Task Detail
Phase | Task | Owner | Start Date | End Date | Duration (days) | Status
0 - Discovery & Design | Inventory and validate all 12 existing appliances (site, IP, policy bindings, RADIUS clients) | Team | 2026-09-01 | 2026-09-07 | 7 | Not Started
0 - Discovery & Design | Confirm target site placement for 6 new appliances (consolidation ratio, HA design) | Michael + Team | 2026-09-01 | 2026-09-14 | 14 | Not Started
0 - Discovery & Design | Define Jamf/Intune API integration requirements | Assigned engineer | 2026-09-08 | 2026-09-14 | 7 | Not Started
0 - Discovery & Design | Define Tanium/Qualys/CrowdStrike re-integration requirements | Assigned engineer | 2026-09-08 | 2026-09-14 | 7 | Not Started
0 - Discovery & Design | Design Ping SAML integration (metadata exchange, attribute mapping) | Assigned engineer | 2026-09-08 | 2026-09-21 | 14 | Not Started
0 - Discovery & Design | Design NiFi ingestion flows and Splunk index/sourcetype strategy | Assigned engineer | 2026-09-15 | 2026-09-21 | 7 | Not Started
0 - Discovery & Design | Define RADIUS MAB template requirements (device classes, fallback policy) | Assigned engineer | 2026-09-15 | 2026-09-21 | 7 | Not Started
0 - Discovery & Design | Define Palo Alto egress FW integration mechanism (User-ID vs. tag/EDL) | Assigned engineer + PA team | 2026-09-15 | 2026-09-28 | 14 | Not Started
0 - Discovery & Design | Define DHCP forwarding requirements per switch platform | Assigned engineer + Switching team | 2026-09-15 | 2026-09-28 | 14 | Not Started
0 - Discovery & Design | Schedule Armis technical architecture review to resolve open RAPD items | Michael | 2026-09-01 | 2026-09-14 | 14 | Not Started
0 - Discovery & Design | Confirm Cisco Catalyst Center licensing (Rogue Management/aWIPS) and WLC/9800 versions | Assigned engineer + Catalyst Center/wireless team | 2026-09-15 | 2026-09-28 | 14 | Not Started
0 - Discovery & Design | Confirm with GRC that PCI DSS v4.0 Req 11.2 maps to a Forescout + Catalyst Center model | Michael + GRC | 2026-09-15 | 2026-09-28 | 14 | Not Started
0 - Discovery & Design | Build cutover and rollback plan per site | Michael | 2026-09-22 | 2026-09-28 | 7 | Not Started
1 - New Hardware Deployment | Procure/stage 6 new appliances | Michael | 2026-09-29 | 2026-10-12 | 14 | Not Started
1 - New Hardware Deployment | Rack, cable, base-OS configuration at target sites | Team | 2026-10-06 | 2026-10-19 | 14 | Not Started
1 - New Hardware Deployment | Apply baseline policy configuration (mirrored from production, pre-integration) | Team | 2026-10-13 | 2026-10-19 | 7 | Not Started
1 - New Hardware Deployment | Establish HA/clustering between new appliances | Assigned engineer | 2026-10-20 | 2026-10-26 | 7 | Not Started
1 - New Hardware Deployment | Validate network reachability (mgmt VLAN, SPAN ports, RADIUS listener) | Team | 2026-10-20 | 2026-11-02 | 14 | Not Started
4 - MFA Admin Access | Register Forescout admin console as SP in PingFederate/PingOne | Assigned engineer + Ping team | 2026-09-29 | 2026-10-12 | 14 | Not Started
4 - MFA Admin Access | Configure SAML assertion attributes (role, group, admin tier) | Assigned engineer | 2026-10-13 | 2026-10-19 | 7 | Not Started
4 - MFA Admin Access | Configure Forescout to accept SAML SSO, enforce MFA at IdP | Assigned engineer | 2026-10-20 | 2026-10-26 | 7 | Not Started
4 - MFA Admin Access | Test MFA login across admin roles | Team | 2026-10-27 | 2026-11-02 | 7 | Not Started
4 - MFA Admin Access | Define break-glass/local-admin fallback procedure | Michael | 2026-10-27 | 2026-11-02 | 7 | Not Started
8 - DHCP Forwarding | Inventory switch platforms and current DHCP relay config per site | Switching team | 2026-10-06 | 2026-10-12 | 7 | Not Started
8 - DHCP Forwarding | Define target DHCP forwarding config (IP helpers, per VLAN) | Assigned engineer + Switching team | 2026-10-13 | 2026-10-19 | 7 | Not Started
8 - DHCP Forwarding | Stage config changes per site (maintenance windows) | Switching team | 2026-10-20 | 2026-11-02 | 14 | Not Started
8 - DHCP Forwarding | Validate Forescout visibility into DHCP lease/fingerprint data | Team | 2026-10-27 | 2026-11-09 | 14 | Not Started
8 - DHCP Forwarding | Rollback/troubleshoot plan per site | Switching team + Michael | 2026-11-03 | 2026-11-09 | 7 | Not Started
2 - Asset Mgmt Integration | Establish API service accounts/app registrations in Jamf and Intune | Assigned engineer | 2026-10-13 | 2026-10-19 | 7 | Not Started
2 - Asset Mgmt Integration | Configure Forescout connectors for Jamf/Intune ingestion | Assigned engineer | 2026-10-20 | 2026-10-26 | 7 | Not Started
2 - Asset Mgmt Integration | Validate device attribute mapping into policy engine | Team | 2026-10-27 | 2026-11-02 | 7 | Not Started
2 - Asset Mgmt Integration | Reconcile Jamf/Intune inventory against Forescout inventory | Team | 2026-11-03 | 2026-11-09 | 7 | Not Started
2 - Asset Mgmt Integration | Resolve discrepancies (orphaned/duplicate/stale entries) | Team | 2026-11-10 | 2026-11-16 | 7 | Not Started
3 - Posture Integration | Re-establish Tanium connector on new appliances | Assigned engineer | 2026-10-13 | 2026-10-19 | 7 | Not Started
3 - Posture Integration | Re-establish Qualys connector | Assigned engineer | 2026-10-20 | 2026-10-26 | 7 | Not Started
3 - Posture Integration | Re-establish CrowdStrike connector | Assigned engineer | 2026-10-20 | 2026-10-26 | 7 | Not Started
3 - Posture Integration | Validate posture data flow into policy decisions | Team | 2026-10-27 | 2026-11-09 | 14 | Not Started
3 - Posture Integration | Parity test vs. legacy stack outcomes | Team | 2026-11-10 | 2026-11-16 | 7 | Not Started
6 - RADIUS MAB Template | Identify device classes requiring MAB | Team | 2026-10-13 | 2026-10-19 | 7 | Not Started
6 - RADIUS MAB Template | Build standardized MAB policy template | Assigned engineer | 2026-10-20 | 2026-10-26 | 7 | Not Started
6 - RADIUS MAB Template | Define exception/onboarding process for post-go-live additions | Michael | 2026-10-27 | 2026-11-02 | 7 | Not Started
6 - RADIUS MAB Template | Test MAB template against sample device classes per site | Team | 2026-11-03 | 2026-11-09 | 7 | Not Started
6 - RADIUS MAB Template | Document template for team/runbook use | Assigned engineer | 2026-11-03 | 2026-11-09 | 7 | Not Started
5 - Logging & Telemetry | Stand up NiFi flow to receive Forescout syslog/API events | Assigned engineer | 2026-10-13 | 2026-10-19 | 7 | Not Started
5 - Logging & Telemetry | Build NiFi processors (parsing, enrichment, routing) | Assigned engineer | 2026-10-20 | 2026-11-02 | 14 | Not Started
5 - Logging & Telemetry | Configure Splunk index(es)/sourcetypes | Assigned engineer + Splunk team | 2026-10-27 | 2026-11-02 | 7 | Not Started
5 - Logging & Telemetry | Validate end-to-end delivery with sample events | Team | 2026-11-03 | 2026-11-09 | 7 | Not Started
5 - Logging & Telemetry | Build baseline dashboards/alerts | Assigned engineer | 2026-11-10 | 2026-11-16 | 7 | Not Started
5 - Logging & Telemetry | Decommission legacy/ad hoc logging path | Team | 2026-11-17 | 2026-11-23 | 7 | Not Started
7 - Palo Alto Egress FW | Confirm context-sharing mechanism (User-ID / DAG-tag / EDL) | Assigned engineer + PA team | 2026-10-27 | 2026-11-02 | 7 | Not Started
7 - Palo Alto Egress FW | Configure Forescout to publish posture-based tags on state change | Assigned engineer | 2026-11-03 | 2026-11-09 | 7 | Not Started
7 - Palo Alto Egress FW | Configure PA egress policy keyed to Forescout tags | PA/firewall team | 2026-11-10 | 2026-11-16 | 7 | Not Started
7 - Palo Alto Egress FW | Validate enforcement — non-compliant/quarantined restriction | Team | 2026-11-17 | 2026-11-23 | 7 | Not Started
7 - Palo Alto Egress FW | Validate enforcement — compliant endpoints retain access | Team | 2026-11-17 | 2026-11-23 | 7 | Not Started
7 - Palo Alto Egress FW | Load/scale test tag propagation latency (validation only — freeze window) | Assigned engineer | 2026-11-24 | 2026-12-07 | 14 | Not Started
11 - RAPD Detection Enablement | Confirm Forescout switch-layer visibility extends to DHCP lease-data integration and covers retail-store infra outside Catalyst Center scope | Assigned engineer + Switching team | 2026-11-10 | 2026-11-16 | 7 | Not Started
11 - RAPD Detection Enablement | Establish correlation mechanism between Forescout switch-port MAC visibility and Catalyst Center RF-layer rogue candidates | Assigned engineer + Catalyst Center/wireless team | 2026-11-17 | 2026-11-23 | 7 | Not Started
11 - RAPD Detection Enablement | Route RAPD detection events through the NiFi/Splunk pipeline for SOC alerting (MAC, BSSID, location, timestamp, classification) | Assigned engineer | 2026-11-17 | 2026-11-23 | 7 | Not Started
11 - RAPD Detection Enablement | Validate detect-notify-investigate-remediate workflow end-to-end against a test rogue scenario (validation only — freeze window) | Team | 2026-11-24 | 2026-12-07 | 14 | Not Started
11 - RAPD Detection Enablement | Document Armis-to-Forescout/Catalyst-Center transition state; confirm with GRC it satisfies PCI DSS 11.2/12.10.1 | Michael + GRC | 2026-11-24 | 2026-12-07 | 14 | Not Started
9 - Cutover | Site-by-site cutover from 12-appliance to 6-appliance footprint | Team | 2027-01-05 | 2027-01-11 | 7 | Not Started
9 - Cutover | Migrate live RADIUS enforcement (802.1X + MAB) to new appliances | Team | 2027-01-05 | 2027-01-11 | 7 | Not Started
9 - Cutover | Cut over DHCP forwarding, egress FW enforcement, logging pipeline per site | Team | 2027-01-12 | 2027-01-18 | 7 | Not Started
9 - Cutover | Monitor for enforcement gaps during parallel-run window | Team | 2027-01-05 | 2027-01-25 | 21 | Not Started
9 - Cutover | Confirm no authentication/posture/egress regressions per site | Team | 2027-01-19 | 2027-01-25 | 7 | Not Started
10 - Decommission | Confirm no active dependencies remain on the 12 legacy appliances | Michael | 2027-01-26 | 2027-02-01 | 7 | Not Started
10 - Decommission | Remove legacy appliances from Panorama/management, network, monitoring | Team | 2027-02-02 | 2027-02-08 | 7 | Not Started
10 - Decommission | Physical decommission (power down, de-rack, asset disposition) | Team | 2027-02-09 | 2027-02-15 | 7 | Not Started
10 - Decommission | Update CMDB/inventory records to reflect final 6-appliance state | Assigned engineer | 2027-02-09 | 2027-02-15 | 7 | Not Started

## Gantt Chart
Workstream | 2026-09-01 | 2026-09-08 | 2026-09-15 | 2026-09-22 | 2026-09-29 | 2026-10-06 | 2026-10-13 | 2026-10-20 | 2026-10-27 | 2026-11-03 | 2026-11-10 | 2026-11-17 | 2026-11-24 | 2026-12-01 | 2026-12-08 | 2026-12-15 | 2026-12-22 | 2026-12-29 | 2027-01-05 | 2027-01-12 | 2027-01-19 | 2027-01-26 | 2027-02-02 | 2027-02-09
0 - Discovery & Design | bar: 2026-09-01 to 2026-09-22
1 - New Hardware Deployment (6 appliances) | bar: 2026-09-29 to 2026-10-27
4 - MFA Admin Access (SAML/Ping) | bar: 2026-09-29 to 2026-10-27
8 - DHCP Forwarding Integration w/ Switching | bar: 2026-10-06 to 2026-11-03
2 - Asset Mgmt Integration (Jamf + Intune) | bar: 2026-10-13 to 2026-11-10
3 - Posture Integration (Tanium/Qualys/CrowdStrike) | bar: 2026-10-13 to 2026-11-10
6 - RADIUS MAB Configuration Template | bar: 2026-10-13 to 2026-11-03
5 - Logging & Telemetry (NiFi + Splunk) | bar: 2026-10-13 to 2026-11-17
7 - Palo Alto Egress FW Integration | bar: 2026-10-27 to 2026-12-01
11 - RAPD Detection Enablement (Forescout + Catalyst Center) | bar: 2026-11-10 to 2026-12-01
Change Freeze / Stabilization Window | bar: 2026-11-24 to 2026-12-29
9 - Cutover (all sites) | bar: 2027-01-05 to 2027-01-19
10 - Decommission (12 legacy appliances) | bar: 2027-01-26 to 2027-02-09
Legend:
Active workstream | bar: 2026-09-01
Change freeze / stabilization window | bar: 2026-09-01

## Risks
Risk | Impact | Mitigation
12→6 consolidation undersizes capacity at high-density sites | Enforcement gaps, performance degradation | Validate throughput/session capacity in Phase 0 before hardware order is finalized
Jamf/Intune data mapping mismatches with Forescout policy logic | False posture decisions, access denials | Reconciliation and parity testing before cutover
Ping SAML misconfiguration locks out admin access | Loss of NAC management during cutover | Break-glass fallback tested before Phase 9
Posture connector re-establishment introduces stale/duplicate data | Incorrect enforcement decisions | Parity test against legacy outcomes before go-live
NiFi/Splunk pipeline lag under high event volume | Blind spots in enforcement visibility | Load-test in Phase 5; keep legacy logging live until validated
MAB template misclassifies a device | Security exposure or endpoint outage | Test against representative samples per site; documented exception path
PA tag/group propagation delay | Temporary over-/under-enforcement at egress | Load/scale test in Phase 7; agree acceptable latency threshold with PA team
DHCP forwarding change disrupts endpoint connectivity | Site-wide outage | Stage in maintenance windows; per-site rollback plan
Change freeze compresses effective working time to ~19 of 24 weeks | Schedule pressure if any phase slips into Nov 24–Jan 4 | Phases 0–8 sequenced to complete by Dec 7, leaving the freeze window as buffer, not critical path
Site cutover sequencing gap across multiple integrated systems | Temporary loss of enforcement/visibility | Parallel-run window per site; no legacy appliance removed until all systems confirmed stable
Cisco Catalyst Center's wired correlation only works for Catalyst-Center-managed switches | Blind spot for non-Cisco and retail-store infrastructure | Forescout's vendor-independent port-level visibility (Phase 11) is the compensating control, not optional
RAPD alternative not yet validated with Armis or GRC before adoption | Risk of building against an unconfirmed compliance mapping | Phase 0 Armis architecture review and GRC confirmation must close before Phase 11 is treated as final

## Open Items
# | Open Item / Decision Needed | Owner | Status
1 | Confirm final site placement/HA design for the 6 new appliances | TBD | Open
2 | Confirm procurement lead time for new hardware (assumed to fit Sep 29–Oct 12; if longer, Phase 1 and overlapping phases shift right) | TBD | Open
3 | Confirm Ping environment (PingFederate on-prem vs. PingOne cloud) | TBD | Open
4 | Confirm break-glass admin access policy owner (Security Engineering vs. IAM) | TBD | Open
5 | Confirm Forescout → Palo Alto context-sharing mechanism | TBD | Open
6 | Confirm Splunk index ownership/retention requirements | TBD | Open
7 | Confirm switch platform inventory and whether DHCP forwarding needs a broader change window | TBD | Open
8 | Confirm final device-class list requiring RADIUS MAB | TBD | Open
9 | Confirm whether the Nov 24–Jan 4 change freeze assumption is accurate for this environment | TBD | Open
10 | Resolve open Armis items via technical architecture review (correlation mechanism, containment capability, licensed module name) before treating Armis transition as decided | TBD | Open
11 | Confirm Cisco Catalyst Center licensing and required WLC/9800 software versions across the estate | TBD | Open
12 | Confirm GRC concurrence that Forescout + Catalyst Center satisfies PCI DSS v4.0 Requirement 11.2 / 12.10.1 | TBD | Open
13 | Confirm whether the current retail-store control model (no dedicated RF sensor; Forescout NAC + 802.1X/DHCP snooping) remains acceptable or needs revisiting | TBD | Open

## Team & Ownership
Role | Name / Group | Responsibility
Program Owner | Michael J. Martin | Cutover/decommission sign-off, cross-team engagement lead
Engineer | Art | Task execution across hardware, integration, and cutover workstreams
Engineer | Joe | Task execution across hardware, integration, and cutover workstreams
Engineer | John | Task execution across hardware, integration, and cutover workstreams
Cross-functional dependency | Splunk/NiFi platform team | Logging pipeline design and index configuration
Cross-functional dependency | Palo Alto/firewall team | Egress FW policy configuration and validation
Cross-functional dependency | Switching team | DHCP forwarding configuration across switch infrastructure
Cross-functional dependency | Ping/IAM team | SAML SSO/MFA integration for admin access